## Gantt Chart
SuitUP! | [7 empty] | Gantt Chart Template © 2020 by Vertex42.com
Company Name | [5 empty] | Project Start: | 2021-06-01
Project Manager:Aleksja Braka | [6 empty] | 1 | time axis 2021-05-31 to 2021-08-01
WBS | Task Name | Feature Type | PROGRESS |  | START | DAYS | END | time axis 2021-05-31 to 2021-08-01
| Sprint 1 | Demand Gathering |  | - | 2021-06-01 |  | 2021-06-14
1.2.1 | Feature 1 | Demand Gathering |  | - | 2021-06-01 | 5 | 2021-06-05
1.1.1 | Feature 2 | Server Requirements | 100% |  | 2021-06-06 | 5 | 2021-06-10
1.1.2 | Feature 3 | Client Requirements |  | - | 2021-06-11 | 4 | 2021-06-14
| Sprint 2 | Planning |  | - | 2021-06-15 |  | 2021-06-28
1.2.1 | Feature 4 | Planning |  | - | 2021-06-15 | 3 | 2021-06-17
1.2.1 | Feature 5 | Implement WBS |  | - | 2021-06-18 | 3 | 2021-06-20
1.2.2 | Feature 6 | Implement Project Schedule | 50% |  | 2021-06-21 | 2 | 2021-06-22
1.2.3 | Feature 7 | Implement Project Resource Plan |  | - | 2021-06-23 | 2 | 2021-06-24
1.2.4 | Feature 8 | Implement Risk Register |  | - | 2021-06-25 | 2 | 2021-06-26
1.2.5 | Feature 9 | Implement Quality Plan | 100% |  | 2021-06-27 | 2 | 2021-06-28
| Sprint 3 | execution |  | - | 2021-06-29 |  | 2021-07-12
1.3 | Feature 10 | Execution |  |  | 2021-06-29 | 2 | 2021-06-30
1.3.1 | Feature 11 | Implement User Friendly Interface |  | - | 2021-07-01 | 2 | 2021-07-02
1.3.2 | Feature 12 | Improve Performance | 50% |  | 2021-07-03 | 2 | 2021-07-04
1.3.2.1 | Feature 13 | Support Web Development |  | - | 2021-07-05 | 2 | 2021-07-06
1.3.2.2 | Feature 14 | Support Integration for Both IOS and Android |  | - | 2021-07-07 | 2 | 2021-07-08
1.3.3 | Feature 15 | Integration of Oracle Live Chat Company |  | - | 2021-07-09 | 2 | 2021-07-10
1.3.4 | Feature 13 | Implement Evaluation Criteria | 50% |  | 2021-07-11 | 2 | 2021-07-12
| Sprint 4 | Testing |  | - | 2021-07-13 |  | 2021-07-26
1.4 | Feature 14 | Testing |  |  | 2021-07-13 | 2 | 2021-07-14
1.4.1 | Feature 15 | Client Testing |  | - | 2021-07-15 | 3 | 2021-07-17
1.4.2 | Feature 16 | Implement Continuously Working Test Sıtes | 50% |  | 2021-07-18 | 3 | 2021-07-20
1.4.3 | Feature 17 | Integration Testing |  | - | 2021-07-21 | 3 | 2021-07-23
1.4.4 | Feature 18 | Testing Security Issues |  | - | 2021-07-24 | 3 | 2021-07-26
| Sprint 5 | Closeout |  | - | 2021-07-27 |  | 2021-08-09
1.5 | Feature 19 | Closeout |  |  | 2021-07-27 | 3 | 2021-07-29
1.5.1 | Feature 20 | Closeout Meeting |  | - | 2021-07-30 | 3 | 2021-08-01
1.5.2 | Feature 21 | Documentation of The Project | 50% |  | 2021-08-02 | 3 | 2021-08-04
1.5.3 | Feature 22 | Implement Closeout Report |  | - | 2021-08-05 | 3 | 2021-08-07
1.5.4 | Feature 23 | Archive The Project | 50% |  | 2021-08-08 | 2 | 2021-08-09

## Help
Help
Instead of detailed help worksheet, please do the following if you have questions about how this spreadsheet works, or how to use this spreadsheet.
1) Watch the Video Tutorial on YouTube
https://youtu.be/8eKk0M2zGIk
2) Read the Following Page
https://www.vertex42.com/ExcelTemplates/simple-gantt-chart.html
Although the content on the above page was created originally for the Excel template, most of the information about the use of formulas and ways to customize the Gantt chart apply just as well to the Google Sheets version.

## TermsOfUse
Simple Gantt Chart for Google Sheets
https://www.vertex42.com/ExcelTemplates/simple-gantt-chart.html
© 2020 Vertex42 LLC. All rights reserved.
This template is a copyrighted work under the Unites States and other copyright laws and is the property of Vertex42 LLC. The items listed below are additional points to help clarify how you may use this template.
You may make archival copies and customize this template only for your personal use or use within your company or organization and not for resale or public sharing.
You may not remove or alter any logo, trademark, copyright, disclaimer, brand, terms of use, attribution, or other proprietary notices or marks within this template.
This template and any customized or modified version of this template may NOT be sold, distributed, published to an online gallery, hosted on a website, or placed on a public server.
The Share Settings for this spreadsheet must always be set to "Private"
Limited Private Sharing and Other Allowed Uses
See the complete license agreement to learn more about how you may or may not use this template.
View the Complete License Agreement
https://www.vertex42.com/licensing/EULA_privateuse.html

## GanttChartPro
Gantt Chart Template Pro for Google Sheets
Gantt Chart Template Pro, by Vertex42.com, is a spreadsheet template designed originally for Microsoft Excel that offers more features than the free version. When you purchase it, you will also get a link to download the Pro version for Google Sheets!!
Learn More About Gantt Chart Template Pro
- Visit the web page above to view screenshots and watch demo videos
Features in the Pro version for Google Sheets
Define task durations by specifying the number of Work Days
- In this free version, the inputs to define a task are the Start Date and the Calendar Day duration. In the Pro version, the default option is to enter the Start Date and the number of Work Days.
Choose whether to define task durations using Calendar Days or Work Days or End Dates
- The Pro version includes a larger set of template rows that provide more options for defining the Start date, End date, duration, and dependency of tasks.
Exclude holidays from work days
- List holidays and other non-working days in a separate sheet. When defining task durations using Work Days, these dates will be excluded.
Define what you mean by "Weekend" when using Work Days
- The Pro version allows you to define exactly which day(s) of the week you want to use as your weekend. The default is Saturday and Sunday.
Color-Code bars in the Gantt chart
- The Pro version includes a column for entering a color code like "k", "r", or "y" to change the color of the bars in the Gantt chart. The Help worksheet explains some advanced formulas that you could use in the Color column to automatically color a bar based on the name in the Lead column.
Define tasks dependences by specifying the predecessor WBS
- The template rows include an option for entering a Predecessor WBS. The Start date will be calculated as the day following the End date of the predecessor.